## Sheet1
Sr no | Project Name | Epic ID | Epic | Story ID | Story Title | Story Description | Task ID | Task | Description | ETA(hrs) | Sub Task | ETA(hrs) | Sprint Number | Sprint Name | Priority | 8 | 5 | 40 | 160
- | IMS | EP-1 | Authentication & Authorization | ST-1.1 | Admin Authentication | Implement secure admin authentication system with role-based access control | ERT-1.1.1 | Implement Admin login API | Create secure REST API for admin authentication with JWT tokens, password hashing, and rate limiting | 16 | Database schema design for admin users | 4 | 1 | Sprint 1 | High
[11 empty] | JWT token implementation | 6
[11 empty] | Password hashing and validation | 4
[11 empty] | Rate limiting implementation | 2
[7 empty] | ERT-1.1.2 | Create Admin login UI | Design and implement responsive admin login interface with form validation and error handling | 12 | Login form design and layout | 4
[11 empty] | Form validation implementation | 4
[11 empty] | Error handling and user feedback | 2
[11 empty] | Responsive design implementation | 2
[7 empty] | ERT-1.1.3 | Role-based access control for Admin | Implement role-based permissions system with admin, super admin, and moderator roles | 20 | Role hierarchy design | 4
[11 empty] | Permission matrix implementation | 8
[11 empty] | Access control middleware | 6
[11 empty] | Role assignment system | 2
|  |  |  | ST-1.2 | Employee Authentication | Implement employee authentication with department-based access control | ERT-1.2.1 | Implement Employee login | Create employee authentication API with department validation and session management | 14 | Employee database schema | 3
[11 empty] | Department validation logic | 4
[11 empty] | Session management system | 4
[11 empty] | Authentication API endpoints | 3
[7 empty] | ERT-1.2.2 | Add employee role permissions | Implement department-specific permissions and access control for employees | 16 | Department permission mapping | 6
[11 empty] | Permission inheritance system | 6
[11 empty] | Access control implementation | 4
|  |  |  | ST-1.3 | Agent Registration & Authentication | Implement agent registration and authentication system | ERT-1.3.1 | Create Agent registration form | Design and implement agent registration form with validation and approval workflow | 18 | Registration form design | 6 | 2 | Sprint 2 | Medium
[11 empty] | Form validation rules | 4
[11 empty] | Document upload integration | 4
[11 empty] | Approval workflow setup | 4
[7 empty] | ERT-1.3.2 | Agent login authentication | Implement agent login system with commission tracking integration | 12 | Agent authentication API | 6
[11 empty] | Commission tracking integration | 4
[11 empty] | Session management | 2
|  |  |  | ST-1.4 | Customer Registration & OTP Authentication | Implement customer registration with OTP verification | ERT-1.4.1 | Integrate OTP service (SMS/Email) | Integrate third-party OTP service for SMS and email verification | 20 | OTP service provider setup | 6
[11 empty] | SMS integration implementation | 8
[11 empty] | Email integration implementation | 6
[7 empty] | ERT-1.4.2 | Create Customer registration form | Design and implement customer registration form with OTP verification flow | 16 | Registration form design | 6
[11 empty] | OTP input interface | 4
[11 empty] | Form validation and submission | 4
[11 empty] | User experience optimization | 2
[7 empty] | ERT-1.4.3 | Verify & store OTP session | Implement OTP verification logic and session management for customers | 14 | OTP verification logic | 6
[11 empty] | Session storage system | 4
[11 empty] | Verification timeout handling | 4
|  | EP-2 | Customer Management System | ST-2.1 | Customer Profile Management | Implement comprehensive customer profile management system | ERT-2.1.1 | Design customer profile database schema | Design normalized database schema for customer profiles with relationships | 12 | Customer basic info table design | 3 | 3 | Sprint 3 | High
[11 empty] | Address management tables | 3
[11 empty] | Contact information tables | 3
[11 empty] | Profile relationships design | 3
[7 empty] | ERT-2.1.2 | Implement profile editing API | Create REST API for customer profile CRUD operations with validation | 18 | Profile creation API | 6 | 3 | Sprint 3 | High
[11 empty] | Profile update API | 6
[11 empty] | Profile retrieval API | 4
[11 empty] | Data validation middleware | 2
[7 empty] | ERT-2.1.3 | Implement document management for profiles | Integrate document upload and management system for customer profiles | 24 | Document upload API | 8 | 3 | Sprint 3 | High
[11 empty] | Document storage integration | 8
[11 empty] | Document retrieval system | 4
[11 empty] | Document metadata management | 4
|  |  |  | ST-2.2 | Document Management System | Implement comprehensive document management with Cloudinary integration | ERT-2.2.1 | Design document management schema | Design database schema for document storage, metadata, and versioning | 16 | Document table design | 4 | 4 | Sprint 4 | Medium
[11 empty] | Metadata tables design | 4
[11 empty] | Version control tables | 4
[11 empty] | Access control tables | 4
[7 empty] | ERT-2.2.2 | Implement Cloudinary integration | Integrate Cloudinary service for document storage and CDN delivery | 20 | Cloudinary configuration setup | 4 | 4 | Sprint 4 | Medium
[11 empty] | File upload service | 8
[11 empty] | File download service | 4
[11 empty] | CDN delivery optimization | 4
[7 empty] | ERT-2.2.3 | Implement document type validation | Add file type validation and security checks for document uploads | 12 | File type validation | 4 | 4 | Sprint 4 | Medium
[11 empty] | Security scanning | 4
[11 empty] | Malware detection | 4
[7 empty] | ERT-2.2.4 | Implement file size restrictions | Add file size limits and compression for document storage | 8 | File size validation | 3 | 4 | Sprint 4 | Medium
[11 empty] | File compression logic | 3
[11 empty] | Storage optimization | 2
[7 empty] | ERT-2.2.5 | Implement document status tracking | Add workflow status tracking for document approval and processing | 16 | Status workflow design | 4 | 4 | Sprint 4 | Medium
[11 empty] | Status update API | 6
[11 empty] | Notification system | 4
[11 empty] | Audit trail logging | 2
|  |  |  | ST-2.3 | Policy Application System | Implement policy application and management system | ERT-2.3.1 | Design policy application schema | Design database schema for policy applications and workflows | 14 | Policy application tables | 4 | 5 | Sprint 5 | High
[11 empty] | Workflow state tables | 4
[11 empty] | Application metadata | 3
[11 empty] | Relationship mappings | 3
[7 empty] | ERT-2.3.2 | Implement policy plan selection API | Create API for policy plan browsing and selection | 18 | Policy plan listing API | 6 | 5 | Sprint 5 | High
[11 empty] | Plan comparison API | 6
[11 empty] | Plan details API | 4
[11 empty] | Search and filter API | 2
[7 empty] | ERT-2.3.3 | Create policy application form API | Implement API for policy application submission and validation | 20 | Application submission API | 8 | 5 | Sprint 5 | High
[11 empty] | Form validation logic | 6
[11 empty] | Data processing service | 4
[11 empty] | Error handling system | 2
[7 empty] | ERT-2.3.4 | Implement document submission for policies | Add document upload and validation for policy applications | 16 | Document upload API | 6 | 5 | Sprint 5 | High
[11 empty] | Document validation | 4
[11 empty] | Policy-document linking | 4
[11 empty] | Submission confirmation | 2
[7 empty] | ERT-2.3.5 | Implement application status tracking | Add workflow status tracking for policy applications | 14 | Status tracking API | 6 | 5 | Sprint 5 | High
[11 empty] | Workflow progression logic | 4
[11 empty] | Status notification system | 4
|  |  |  | ST-2.4 | Payment & EMI Management | Implement payment processing and EMI management system | ERT-2.4.1 | Design payment and EMI database schema | Design database schema for payments, EMIs, and transaction history | 16 | Payment tables design | 4 | 6 | Sprint 6 | High
[11 empty] | EMI calculation tables | 4
[11 empty] | Transaction history tables | 4
[11 empty] | Payment status tables | 4
[7 empty] | ERT-2.4.2 | Implement payment gateway integration | Integrate payment gateway (PayPal/Razorpay) for transaction processing | 24 | Payment gateway setup | 6 | 6 | Sprint 6 | High
[11 empty] | Transaction processing API | 8
[11 empty] | Payment confirmation handling | 6
[11 empty] | Error handling and retry logic | 4
[7 empty] | ERT-2.4.3 | Implement EMI calculation logic | Add EMI calculation algorithms and payment scheduling | 18 | EMI calculation algorithms | 8 | 6 | Sprint 6 | High
[11 empty] | Payment scheduling system | 6
[11 empty] | Interest calculation logic | 4
[7 empty] | ERT-2.4.4 | Implement payment history tracking | Add comprehensive payment history and transaction logging | 14 | Payment history API | 6 | 6 | Sprint 6 | High
[11 empty] | Transaction logging service | 4
[11 empty] | History search and filter | 4
[7 empty] | ERT-2.4.5 | Implement receipt generation | Add automated receipt generation and delivery system | 12 | Receipt template design | 4 | 6 | Sprint 6 | High
[11 empty] | Receipt generation service | 4
[11 empty] | Delivery system integration | 4
|  | EP-3 | Agent Management System | ST-3.1 | Agent Profile Management | Implement agent profile and document management system | ERT-3.1.1 | Design agent profile database schema | Design database schema for agent profiles, qualifications, and documents | 14 | Agent basic info tables | 4 | 7 | Sprint 7 | Medium
[11 empty] | Qualification tables | 4
[11 empty] | Document reference tables | 3
[11 empty] | Performance metrics tables | 3
[7 empty] | ERT-3.1.2 | Implement profile editing API | Create REST API for agent profile management and updates | 16 | Profile creation API | 6
[11 empty] | Profile update API | 6
[11 empty] | Profile retrieval API | 4
[7 empty] | ERT-3.1.3 | Implement document updates for agents | Add document management system for agent qualification and compliance | 20 | Document upload API | 8
[11 empty] | Document validation service | 6
[11 empty] | Compliance checking system | 4
[11 empty] | Document approval workflow | 2
|  |  |  | ST-3.2 | Policy Registration for Customers | Implement agent-driven policy registration system | ERT-3.2.1 | Design policy registration schema | Design database schema for agent-customer policy relationships | 12 | Agent-customer mapping tables | 4 | 8 | Sprint 8 | High
[11 empty] | Policy registration tables | 4
[11 empty] | Commission tracking tables | 4
[7 empty] | ERT-3.2.2 | Implement customer selection API | Create API for agents to browse and select customers | 14 | Customer listing API | 6
[11 empty] | Customer search API | 4
[11 empty] | Customer selection service | 4
[7 empty] | ERT-3.2.3 | Implement policy plan selection for agents | Add policy plan browsing and selection interface for agents | 16 | Policy plan listing API | 6
[11 empty] | Plan comparison tools | 6
[11 empty] | Plan recommendation system | 4
[7 empty] | ERT-3.2.4 | Implement commission calculation | Add automated commission calculation based on policy sales | 20 | Commission rate configuration | 6
[11 empty] | Commission calculation engine | 8
[11 empty] | Commission validation logic | 4
[11 empty] | Commission adjustment system | 2
[7 empty] | ERT-3.2.5 | Implement policy status tracking | Add workflow tracking for agent-managed policies | 14 | Policy status API | 6
[11 empty] | Status update service | 4
[11 empty] | Notification system | 4
|  |  |  | ST-3.3 | Commission Management System | Implement comprehensive commission tracking and management | ERT-3.3.1 | Design commission management schema | Design database schema for commission calculations and tracking | 16 | Commission calculation tables | 4 | 9 | Sprint 9 | High
[11 empty] | Commission history tables | 4
[11 empty] | Commission adjustment tables | 4
[11 empty] | Commission rules tables | 4
[7 empty] | ERT-3.3.2 | Implement commission calculation logic | Add automated commission calculation algorithms | 22 | Base commission calculation | 8
[11 empty] | Performance bonus logic | 6
[11 empty] | Commission adjustment logic | 4
[11 empty] | Commission validation service | 4
[7 empty] | ERT-3.3.3 | Implement earnings report generation | Add commission earnings reports and analytics | 18 | Report generation engine | 8
[11 empty] | Data aggregation service | 6
[11 empty] | Report formatting service | 4
[7 empty] | ERT-3.3.4 | Implement withdrawal request system | Add withdrawal request workflow for agent commissions | 16 | Withdrawal request API | 6
[11 empty] | Request validation logic | 4
[11 empty] | Request approval workflow | 4
[11 empty] | Request tracking system | 2
|  |  |  | ST-3.4 | Withdrawal Management | Implement withdrawal approval and processing system | ERT-3.4.1 | Design withdrawal management schema | Design database schema for withdrawal requests and approvals | 14 | Withdrawal request tables | 4 | 10 | Sprint 10 | Medium
[11 empty] | Approval workflow tables | 4
[11 empty] | Payment processing tables | 3
[11 empty] | Audit trail tables | 3
[7 empty] | ERT-3.4.2 | Implement withdrawal request form API | Create API for withdrawal request submission | 12 | Request submission API | 6
[11 empty] | Request validation service | 4
[11 empty] | Request confirmation system | 2
[7 empty] | ERT-3.4.3 | Implement withdrawal status tracking | Add workflow tracking for withdrawal requests | 10 | Status tracking API | 4
[11 empty] | Status update service | 3
[11 empty] | Status notification system | 3
[7 empty] | ERT-3.4.4 | Implement admin approval workflow | Add admin approval system for withdrawal requests | 16 | Approval interface API | 6
[11 empty] | Approval decision logic | 4
[11 empty] | Approval notification system | 4
[11 empty] | Approval audit logging | 2
|  | EP-4 | Employee Management System | ST-4.1 | Document Verification System | Implement document verification and approval workflow | ERT-4.1.1 | Design document verification schema | Design database schema for document verification workflows | 14 | Verification request tables | 4 | 11 | Sprint 11 | High
[11 empty] | Verification status tables | 4
[11 empty] | Verification history tables | 3
[11 empty] | Approval workflow tables | 3
[7 empty] | ERT-4.1.2 | Implement document review interface API | Create API for document review and verification processes | 18 | Document review API | 8
[11 empty] | Review assignment service | 4
[11 empty] | Review status update API | 4
[11 empty] | Review history API | 2
[7 empty] | ERT-4.1.3 | Implement approval/rejection workflow | Add approval/rejection workflow with status tracking | 20 | Approval workflow engine | 8
[11 empty] | Rejection handling logic | 6
[11 empty] | Workflow state management | 4
[11 empty] | Workflow transition logic | 2
[7 empty] | ERT-4.1.4 | Implement status update notifications | Add notification system for document status updates | 12 | Notification service setup | 4
[11 empty] | Email notification system | 4
[11 empty] | In-app notification system | 4
|  |  |  | ST-4.2 | Customer & Agent Data Management | Implement comprehensive data management system | ERT-4.2.1 | Design data management schema | Design database schema for customer and agent data operations | 16 | Data operation tables | 4 | 12 | Sprint 12 | Medium
[11 empty] | Data change history tables | 4
[11 empty] | Data relationship tables | 4
[11 empty] | Data access control tables | 4
[7 empty] | ERT-4.2.2 | Implement data editing capabilities | Add data editing and update functionality for employees | 18 | Data edit API | 8
[11 empty] | Data validation service | 6
[11 empty] | Data update service | 4
[7 empty] | ERT-4.2.3 | Implement search and filter functionality | Add advanced search and filtering for customer/agent data | 20 | Search engine implementation | 8
[11 empty] | Filter system implementation | 6
[11 empty] | Search result ranking | 4
[11 empty] | Search optimization | 2
[7 empty] | ERT-4.2.4 | Implement bulk operations | Add bulk data operations for efficiency | 16 | Bulk update API | 6
[11 empty] | Bulk delete API | 4
[11 empty] | Bulk import service | 4
[11 empty] | Bulk export service | 2
[7 empty] | ERT-4.2.5 | Implement audit trail system | Add comprehensive audit logging for data changes | 14 | Audit logging service | 6
[11 empty] | Change tracking system | 4
[11 empty] | Audit report generation | 4
|  |  |  | ST-4.3 | Commission Report Generation | Implement commission reporting and analytics system | ERT-4.3.1 | Design commission report schema | Design database schema for commission reporting | 12 | Report configuration tables | 4 | 13 | Sprint 13 | Medium
[11 empty] | Report template tables | 4
[11 empty] | Report schedule tables | 4
[7 empty] | ERT-4.3.2 | Implement report generation API | Create API for commission report generation | 18 | Report generation engine | 8
[11 empty] | Data aggregation service | 6
[11 empty] | Report formatting service | 4
[7 empty] | ERT-4.3.3 | Implement data export functionality | Add data export capabilities for reports | 14 | Export service setup | 6
[11 empty] | Multiple format support | 4
[11 empty] | Export scheduling system | 4
[7 empty] | ERT-4.3.4 | Implement filtering options | Add advanced filtering and sorting for reports | 12 | Filter configuration API | 6
[11 empty] | Filter application service | 4
[11 empty] | Filter persistence system | 2
|  | EP-5 | Admin Management System | ST-5.1 | Insurance Plan Management | Implement comprehensive insurance plan management system | ERT-5.1.1 | Design insurance plan database schema | Design database schema for insurance plans, coverage, and pricing | 16 | Insurance plan tables | 4 | 14 | Sprint 14 | High
[11 empty] | Coverage detail tables | 4
[11 empty] | Pricing structure tables | 4
[11 empty] | Plan category tables | 4
[7 empty] | ERT-5.1.2 | Implement plan creation form API | Create API for insurance plan creation and management | 20 | Plan creation API | 8 | 14 | Sprint 14 | High
[11 empty] | Plan update API | 6
[11 empty] | Plan validation service | 4
[11 empty] | Plan approval workflow | 2
[7 empty] | ERT-5.1.3 | Implement premium calculation logic | Add automated premium calculation algorithms | 24 | Base premium calculation | 8 | 14 | Sprint 14 | High
[11 empty] | Risk factor calculation | 8
[11 empty] | Discount calculation logic | 4
[11 empty] | Premium validation service | 4
[7 empty] | ERT-5.1.4 | Implement plan status management | Add plan lifecycle management and status tracking | 14 | Status workflow engine | 6 | 14 | Sprint 14 | High
[11 empty] | Status transition logic | 4
[11 empty] | Status notification system | 4
|  |  |  | ST-5.2 | Commission Settings Management | Implement commission configuration and management system | ERT-5.2.1 | Design commission settings schema | Design database schema for commission configurations | 12 | Commission rate tables | 4 | 15 | Sprint 15 | High
[11 empty] | Commission tier tables | 4
[11 empty] | Commission rule tables | 4
[7 empty] | ERT-5.2.2 | Implement commission rate setting API | Create API for commission rate configuration | 16 | Rate configuration API | 8 | 15 | Sprint 15 | High
[11 empty] | Rate validation service | 4
[11 empty] | Rate approval workflow | 4
[7 empty] | ERT-5.2.3 | Implement tier-based commission structure | Add tier-based commission calculation system | 20 | Tier definition API | 8 | 15 | Sprint 15 | High
[11 empty] | Tier calculation engine | 8
[11 empty] | Tier validation logic | 4
[7 empty] | ERT-5.2.4 | Implement historical tracking | Add commission rate history and change tracking | 14 | History tracking service | 6 | 15 | Sprint 15 | High
[11 empty] | Change notification system | 4
[11 empty] | History report generation | 4
|  |  |  | ST-5.3 | Approval Workflow Management | Implement comprehensive approval workflow system | ERT-5.3.1 | Design approval workflow schema | Design database schema for approval workflows | 16 | Workflow definition tables | 4 | 16 | Sprint 16 | High
[11 empty] | Workflow state tables | 4
[11 empty] | Approval routing tables | 4
[11 empty] | Workflow history tables | 4
[7 empty] | ERT-5.3.2 | Implement withdrawal approval system | Add withdrawal request approval workflow | 18 | Withdrawal approval API | 8 | 16 | Sprint 16 | High
[11 empty] | Approval routing logic | 6
[11 empty] | Approval decision handling | 4
[7 empty] | ERT-5.3.3 | Implement claim approval system | Add insurance claim approval workflow | 20 | Claim approval API | 8 | 16 | Sprint 16 | High
[11 empty] | Claim validation service | 6
[11 empty] | Claim routing logic | 4
[11 empty] | Claim decision handling | 2
[7 empty] | ERT-5.3.4 | Implement document approval system | Add document approval workflow | 16 | Document approval API | 8 | 16 | Sprint 16 | High
[11 empty] | Document routing logic | 4
[11 empty] | Document decision handling | 4
[7 empty] | ERT-5.3.5 | Implement bulk approval operations | Add bulk approval functionality for efficiency | 14 | Bulk approval API | 8 | 16 | Sprint 16 | High
[11 empty] | Bulk validation service | 4
[11 empty] | Bulk notification system | 2
|  |  |  | ST-5.4 | System Reports & Analytics | Implement comprehensive reporting and analytics system | ERT-5.4.1 | Design reporting database schema | Design database schema for analytics and reporting | 18 | Report configuration tables | 6 | 17 | Sprint 17 | Medium
[11 empty] | Analytics data tables | 6
[11 empty] | Report template tables | 3
[11 empty] | Report schedule tables | 3
[7 empty] | ERT-5.4.2 | Implement dashboard analytics API | Create API for dashboard analytics and metrics | 24 | Analytics calculation engine | 10 | 17 | Sprint 17 | Medium
[11 empty] | Real-time data service | 8
[11 empty] | Metrics aggregation service | 6
[7 empty] | ERT-5.4.3 | Implement financial reports generation | Add financial reporting and analysis capabilities | 20 | Financial calculation engine | 8 | 17 | Sprint 17 | Medium
[11 empty] | Report formatting service | 6
[11 empty] | Financial validation service | 4
[11 empty] | Report scheduling system | 2
[7 empty] | ERT-5.4.4 | Implement user activity reports | Add user activity tracking and reporting | 16 | Activity tracking service | 8 | 17 | Sprint 17 | Medium
[11 empty] | Activity aggregation service | 4
[11 empty] | Activity report generation | 4
[7 empty] | ERT-5.4.5 | Implement export capabilities | Add data export functionality for reports | 12 | Export service setup | 6 | 17 | Sprint 17 | Medium
[11 empty] | Multiple format support | 4
[11 empty] | Export scheduling system | 2
|  | EP-6 | Integration Services | ST-6.1 | Email Service Integration | Implement email service integration with SMTP/Gmail | ERT-6.1.1 | Setup SMTP/Gmail configuration | Configure SMTP settings and Gmail API integration | 8 | SMTP server configuration | 3 | 18 | Sprint 18 | Medium
[11 empty] | Gmail API setup | 3
[11 empty] | Email service configuration | 2
[7 empty] | ERT-6.1.2 | Create email templates | Design and implement email templates for various notifications | 16 | Template design system | 6 | 18 | Sprint 18 | Medium
[11 empty] | Template management API | 6
[11 empty] | Template customization service | 4
[7 empty] | ERT-6.1.3 | Implement automated email triggers | Add automated email sending based on system events | 18 | Event trigger system | 8 | 18 | Sprint 18 | Medium
[11 empty] | Email scheduling service | 6
[11 empty] | Email queue management | 4
[7 empty] | ERT-6.1.4 | Implement delivery tracking | Add email delivery tracking and failure handling | 12 | Delivery tracking service | 6 | 18 | Sprint 18 | Medium
[11 empty] | Failure handling logic | 4
[11 empty] | Retry mechanism | 2
|  |  |  | ST-6.2 | OTP Service Integration | Implement OTP service for SMS/Email verification | ERT-6.2.1 | Setup OTP service provider configuration | Configure OTP service provider (Twilio/SendGrid) | 10 | Provider API configuration | 4 | 19 | Sprint 19 | Medium
[11 empty] | Service credentials setup | 3
[11 empty] | Service health monitoring | 3
[7 empty] | ERT-6.2.2 | Implement OTP generation API | Create API for OTP generation and validation | 16 | OTP generation service | 6 | 19 | Sprint 19 | Medium
[11 empty] | OTP validation service | 6
[11 empty] | OTP storage service | 4
[7 empty] | ERT-6.2.3 | Implement SMS/Email delivery | Add SMS and email delivery for OTP codes | 18 | SMS delivery service | 8 | 19 | Sprint 19 | Medium
[11 empty] | Email delivery service | 6
[11 empty] | Delivery confirmation service | 4
[7 empty] | ERT-6.2.4 | Implement verification process | Add OTP verification workflow and session management | 14 | Verification workflow engine | 6 | 19 | Sprint 19 | Medium
[11 empty] | Session management service | 4
[11 empty] | Verification timeout handling | 4
|  |  |  | ST-6.3 | Payment Gateway Integration | Implement payment gateway integration with PayPal/Razorpay | ERT-6.3.1 | Setup PayPal/Razorpay configuration | Configure payment gateway settings and API keys | 12 | Gateway API configuration | 4 | 20 | Sprint 20 | High
[11 empty] | Security key management | 4
[11 empty] | Gateway health monitoring | 4
[7 empty] | ERT-6.3.2 | Implement payment processing API | Create API for payment processing and transaction management | 24 | Payment initiation API | 8 | 20 | Sprint 20 | High
[11 empty] | Payment confirmation handling | 8
[11 empty] | Transaction management service | 6
[11 empty] | Error handling system | 2
[7 empty] | ERT-6.3.3 | Implement transaction logging | Add comprehensive transaction logging and audit trail | 16 | Transaction logging service | 8 | 20 | Sprint 20 | High
[11 empty] | Audit trail service | 4
[11 empty] | Log analysis service | 4
[7 empty] | ERT-6.3.4 | Implement refund handling | Add refund processing and management system | 20 | Refund initiation API | 8 | 20 | Sprint 20 | High
[11 empty] | Refund validation service | 6
[11 empty] | Refund processing logic | 4
[11 empty] | Refund notification system | 2
[7 empty] | ERT-6.3.5 | Implement payment security measures | Add security measures like encryption and fraud detection | 18 | Payment encryption service | 8 | 20 | Sprint 20 | High
[11 empty] | Fraud detection system | 6
[11 empty] | Security monitoring service | 4
|  |  |  | ST-6.4 | Cloud Storage Integration | Implement Cloudinary integration for file management | ERT-6.4.1 | Setup Cloudinary configuration | Configure Cloudinary settings and API integration | 8 | Cloudinary API setup | 4 | 21 | Sprint 21 | Medium
[11 empty] | Storage configuration | 2
[11 empty] | Service health monitoring | 2
[7 empty] | ERT-6.4.2 | Implement file upload API | Create API for file upload to Cloudinary | 16 | File upload service | 8 | 21 | Sprint 21 | Medium
[11 empty] | Upload validation service | 4
[11 empty] | Upload progress tracking | 4
[7 empty] | ERT-6.4.3 | Implement file download API | Create API for file download and access control | 14 | File download service | 6 | 21 | Sprint 21 | Medium
[11 empty] | Access control service | 4
[11 empty] | Download tracking service | 4
[7 empty] | ERT-6.4.4 | Implement storage management | Add file storage management and cleanup | 12 | Storage optimization service | 6 | 21 | Sprint 21 | Medium
[11 empty] | File cleanup service | 4
[11 empty] | Storage analytics service | 2
[7 empty] | ERT-6.4.5 | Implement security controls | Add file access control and security measures | 16 | File access control service | 8 | 21 | Sprint 21 | Medium
[11 empty] | Security scanning service | 4
[11 empty] | Access logging service | 4
|  | EP-7 | Dashboard & UI System | ST-7.1 | Admin Dashboard | Implement comprehensive admin dashboard interface | ERT-7.1.1 | Design admin dashboard UI components | Design responsive admin dashboard components and layout | 24 | Dashboard layout design | 8 | 22 | Sprint 22 | High
[11 empty] | Component library design | 8
[11 empty] | Responsive design system | 4
[11 empty] | Design system documentation | 4
[7 empty] | ERT-7.1.2 | Implement system overview widgets | Create dashboard widgets for system metrics and overview | 20 | Metrics calculation service | 8
[11 empty] | Widget rendering engine | 6
[11 empty] | Real-time data updates | 4
[11 empty] | Widget customization service | 2
[7 empty] | ERT-7.1.3 | Implement quick action buttons | Add quick action buttons for common admin tasks | 16 | Action button component | 6
[11 empty] | Action routing service | 4
[11 empty] | Action confirmation system | 4
[11 empty] | Action history tracking | 2
[7 empty] | ERT-7.1.4 | Implement notification system | Add real-time notification system for admin dashboard | 18 | Notification service setup | 6
[11 empty] | Real-time notification engine | 6
[11 empty] | Notification preferences | 4
[11 empty] | Notification history | 2
|  |  |  | ST-7.2 | Employee Dashboard | Implement employee dashboard interface | ERT-7.2.1 | Design employee dashboard UI | Design responsive employee dashboard layout and components | 20 | Dashboard layout design | 8 | 23 | Sprint 23 | Medium
[11 empty] | Employee-specific components | 6
[11 empty] | Responsive design implementation | 4
[11 empty] | Accessibility features | 2
[7 empty] | ERT-7.2.2 | Implement task overview interface | Create task overview and management interface | 18 | Task listing component | 8
[11 empty] | Task filtering system | 6
[11 empty] | Task status management | 4
[7 empty] | ERT-7.2.3 | Implement document queue interface | Add document queue and processing interface | 16 | Queue display component | 6
[11 empty] | Queue management service | 6
[11 empty] | Priority sorting system | 4
|  |  |  | ST-7.3 | Agent Dashboard | Implement agent dashboard interface | ERT-7.3.1 | Design agent dashboard UI | Design responsive agent dashboard layout and components | 22 | Dashboard layout design | 8 | 24 | Sprint 24 | Medium
[11 empty] | Agent-specific components | 6
[11 empty] | Commission display components | 4
[11 empty] | Performance metrics display | 4
[7 empty] | ERT-7.3.2 | Implement policy overview widgets | Create policy overview and management widgets | 20 | Policy summary widget | 8
[11 empty] | Policy status widget | 6
[11 empty] | Policy action widget | 4
[11 empty] | Policy search widget | 2
[7 empty] | ERT-7.3.3 | Implement commission summary display | Add commission summary and earnings display | 18 | Commission calculation display | 8
[11 empty] | Earnings history chart | 6
[11 empty] | Commission breakdown view | 4
[7 empty] | ERT-7.3.4 | Implement customer list interface | Add customer management interface for agents | 16 | Customer listing component | 6
[11 empty] | Customer search service | 4
[11 empty] | Customer action buttons | 4
[11 empty] | Customer details modal | 2
|  |  |  | ST-7.4 | Customer Dashboard | Implement customer dashboard interface | ERT-7.4.1 | Design customer dashboard UI | Design responsive customer dashboard layout and components | 20 | Dashboard layout design | 8 | 25 | Sprint 25 | Medium
[11 empty] | Customer-specific components | 6
[11 empty] | Responsive design implementation | 4
[11 empty] | User experience optimization | 2
[7 empty] | ERT-7.4.2 | Implement policy overview interface | Create policy overview and management interface | 18 | Policy summary component | 8
[11 empty] | Policy details component | 6
[11 empty] | Policy action buttons | 4
[7 empty] | ERT-7.4.3 | Implement payment history display | Add payment history and transaction display | 16 | Payment history component | 8
[11 empty] | Transaction details view | 4
[11 empty] | Payment status indicators | 4
[7 empty] | ERT-7.4.4 | Implement document access interface | Add document access and management interface | 14 | Document listing component | 6
[11 empty] | Document viewer component | 4
[11 empty] | Document download service | 4
Epic ID | Epic Name | Total Hours | Total Days (8 hrs/day)
EP-1 | Authentication & Authorization | 158 | 20
EP-2 | Customer Management System | 242 | 30
EP-3 | Agent Management System | 220 | 28
EP-4 | Employee Management System | 194 | 24
EP-5 | Admin Management System | 260 | 33
EP-6 | Integration Services | 222 | 28
EP-7 | Dashboard & UI System | 242 | 30
TOTAL | All Epics | 1538 | 193